## equipment
type | name | number | scope
Exchanger | Overhead Accumulater | 12E56A | Open, Clean, Inspect, RFT 100% of tubes, Replace Channel and Channel Cover
Exchanger | Overhead Accumulater | 12E56B | Open, Clean, Inspect, RFT 100% of tubes, Replace Channel and Channel Cover
Exchanger | Overhead Accumulater | 12E56C | Open, Clean, Inspect, RFT 100% of tubes, Replace Channel and Channel Cover
Fin Fan | Overhead Condenser | 12E78A | Open 25% of plugs, Clean, Inspect, RFT 25%
Fin Fan | Overhead Condenser | 12E78B | Open 25% of plugs, Clean, Inspect, RFT 25%
Fin Fan | Overhead Condenser | 12E78C | Open 25% of plugs, Clean, Inspect, RFT 25%
Drum | Flash Drum | 12V23 | Open, clean, inspect, WFMT 100% internal weld seams. Replace demister
Drum | Flare Drum | 65V23 | Grit blast 100% internal surfaces, WFMT 50% weld seams. Recoat,
Tower | Crude Column | 12V7 | Open, clean, inspect. Replace trays 34-50
Tower | Vac Column | 13V78 | Open, clean, inspect. Replace packing beds and hardware.
Heater | Crude Heater | 12H76 | Cursory only, no scaffolding, inspect from floor unless inspection needs further evaluation. Replace burner tiles

## components
number | name
12E56A | External, Shell, Shell Cover, Channel, Channel Cover, Bundle, Floating Head/Split Rings, Closure, Hydro, Report
12E56B | External, Shell, Shell Cover, Channel, Channel Cover, Bundle, Floating Head/Split Rings, Closure, Hydro, Report
12E56C | External, Shell, Shell Cover, Channel, Channel Cover, Bundle, Floating Head/Split Rings, Closure, Hydro, Report
12E78A | External, Header Boxes, Tubesheets, Tubes, Closure, Hydro, Report
12E78B | External, Header Boxes, Tubesheets, Tubes, Closure, Hydro, Report
12E78C | External, Header Boxes, Tubesheets, Tubes, Closure, Hydro, Report
12V23 | External, Shell, Heads, Internal Components, Closure, Report
65V23 | External, Shell, Heads, Internal Components, Closure, Report
12V7 | External, Shell, Heads, Internal Components, Closure, Report
13V78 | External, Shell, Heads, Internal Components, Closure, Report
12H76 | External, Radiant Mechanical, Radiant Refractory, Convection Mechanical, Convection Refractory, Stack, Closure, Report

## methods
number | name
12E56A | External, VT; Shell, VT; Shell Cover, VT; Channel, VT; Channel Cover, VT; Bundle, VT, RFT; Floating Head/Split Rings, VT; Closure, Ok to Install Bundle; Hydro, Shell Side, Tube Side; Report, Complete;
12E56B | External, VT; Shell, VT; Shell Cover, VT; Channel, VT; Channel Cover, VT; Bundle, VT, RFT; Floating Head/Split Rings, VT; Closure, Ok to Install Bundle; Hydro, Shell Side, Tube Side; Report, Complete;
12E56C | External, VT; Shell, VT; Shell Cover, VT; Channel, VT; Channel Cover, VT; Bundle, VT, RFT; Floating Head/Split Rings, VT; Closure, Ok to Install Bundle; Hydro, Shell Side, Tube Side; Report, Complete;
12E78A | External, VT; Header Boxes, VT; Tubesheets, VT; Tubes, VT, RFT; Closure, Ok to Install Plugs; Hydro, Complete; Report, Complete;
12E78B | External, VT; Header Boxes, VT; Tubesheets, VT; Tubes, VT, RFT; Closure, Ok to Install Plugs; Hydro, Complete; Report, Complete;
12E78C | External, VT; Header Boxes, VT; Tubesheets, VT; Tubes, VT, RFT; Closure, Ok to Install Plugs; Hydro, Complete; Report, Complete;
12V23 | External, VT; Shell, VT, WFMT; Heads, VT, WFMT; Internal Components, VT; Closure, Ok to Close; Report, Complete
65V23 | External, VT; Shell, VT, WFMT; Heads, VT, WFMT; Internal Components, VT; Closure, Ok to Close; Report, Complete
12V7 | External, VT; Shell, VT, WFMT; Heads, VT, WFMT; Internal Components, VT; Closure, Ok to Close Internal Manways, Ok to Close External Manways; Report, Complete
13V78 | External, VT; Shell, VT, WFMT; Heads, VT, WFMT; Internal Components, VT; Closure, Ok to Close Internal Manways, Ok to Close External Manways; Report, Complete
12H76 | External, VT; Radiant Mechanical, VT; Radiant Refractory, VT; Convection Mechanical, VT; Convection Refractory, VT; Stack, VT; Closure, Ok to Close; Report, Complete